## Feuil1
Task | Details | Started on | Finished On | Status | Comments | Remarks | Possible Status
Install GNU Radio 3.6.5 | Version 3.6 with UHD using the build-gnuradio script | 2013-05-27 | 2013-05-02 | Complete | Need to be changed to 3,7 |  | Complete
Install gr-ieee80211 | Using the GIT repo | 2013-05-27 | 2013-05-02 | Complete |  |  | Processing
Revisit the Goals | Define the goals properly | 2013-05-27 | 2013-06-07 | Processing |  |  | Resolving an issue
Complete the Project Hosting | Get everything up on the Google Code Project | 2013-05-27 |  | Complete
Switching to GNU Radio 3.7 | Change the version for compatibility issues | 2013-06-03 |  | Complete | Need to uninstall each module of 3.6.5 carefully
Pseudo Random PDU | Not Reaquired
Libpcap Study | Done, quite good way
OFDM Code Commenting | Understanding the code from Innsbruck guys | 2013-06-02 |  | Complete | Almost
PCAP Block
Libpcap development